Project schedule

---
Project schedule
- Most concrete part of project planning
- Baseline for execution of the project
- Sometimes ”scheduling time” = ”execution time”

---
Project schedule
- Define activities
- Describe dependencies
- Estimate resources
- Estimate durations
- Develop the schedule

---
Define activities
- Activity list (based on WBS)
- Activity attributes
- Milestone list

---
Describe dependencies
- Logical connections between activities
- Directed acyclic graph
- A → B
  ”A needs to be completed before B is started ”
Start
Design DB
Design UI
Implement UI
Implement DB
Business
logic
Deploy
Finish
Configure DB server

---
Estimate resources
- Resource calendars
- Develop resource breakdown structure (RBS)
- Helps to estimate durations

---
Estimate durations
- Expert judgment (ask the tech guys)
- Analogous estimate (look at previous projects)
- Three-point estimates (the good, the bad and the realistic)
- Parametric estimate (use a calculator)
- Take risks into account

---
The schedule
- PERT charts
- Critical path method
- Gantt charts

---
PERT charts
- Show activity dependencies
- Show expected activity duration
- Optimistic time (O)
- Pessimistic time (P)
- Most likely time (M)
- Expected time
left (T_E = {O + 4M + P} over {6} right )

---
Critical path method
- Early start (ES)
- Early finish (EF)
- ES(start) = 0
- EF(A) = ES(A) + duration(A)
- ES(A) = max { EF(B) | B → A }

---
Critical path method
- Late start (LS)
- Late finish (LF)
- LF(end) = EF(end)
- LS(A) = LF(A) – duration(A)
- LF(A) = min { LS(B) | A → B }

---
Critical path method
- Slack (S)
- S(A) = LS(A) – ES(A) = LF(A) – EF(A)
- A is critical ↔ S(A) = 0
ES	Duration	EF
Task name
EF	Slack	LF

---
Gantt chart
- Activities are bars on a time grid
- High level of detail
- Different link types
- Constraints
- Activity hierarchy
- Weekends and holidays
- Resource allocation
- Progress monitoring

---
Gantt chart
- Common for presenting to wide audience
- Not very useful for really large projects
- Usually prepared with a software tool
  - Microsoft Project
  - GanttProject.biz
  - Microsoft Excel
  - ...
Time for a demo!

---
Schedule adjustment
- Critical chain method
- Resource levelling
- What if … ?
- Schedule compression

---
Questions?